## Clinton (CA)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | RMFP | NFP | NFI | NDJ | NVJ | RI | DLG | DLNG | DTG | DTNG
1 | STUDY | 12108 | 01001A
1 | 101 |  | 01002A
1 | CA01010 | 25918 | 01002A
1 | 102-0 |  | 01003A
1 | 102-1 |  | 01004A
1 | 102-2 |  | 01005A
1 | 103-0 | 12108 | 01006A
1 | 103-0 |  | 01007A
1 | 103-0 |  | 01008A | [7 empty] | video short
1 | 103-1 |  | 01009A
1 | 103-2 |  | 01010A
1 | 104-0 | 12059 | 01011A | [6 empty] | Missing | Room was occupied when replacing red phone |  | YES
1 | 104-0 |  | 01012A
1 | 104-1 |  | 01013A
1 | 104-2 |  | 01014A
1 | 105-0 | 12087 | 01015A
1 | 105-0 |  | 01016A | [7 empty] | video short
1 | 105-1 |  | 01017A | [7 empty] | video short
1 | 105-2 |  | 01018A | [7 empty] | video short
1 | 106-0 | 12072 | 01019A
1 | 106-0 |  | 01020A | [5 empty] | No Cxn |  |  | YES | YES | [9 empty] | 1
1 | 106-0 |  | 01021A
1 | 106-1 |  | 01022A
1 | 106-2 |  | 01023A
1 | 106-3 |  | 01024A
1 | 107-0 |  | 01025A
1 | 107-0 | 12068 | 01026A
1 | 107-0 |  | 01027A
1 | 107-1 |  | 01028A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1 | 1 | 1 | 1 |  | 1
1 | 107-2 |  | 01029A | [5 empty] | In |  |  | YES | YES | [6 empty] | 1
1 | 107-3 |  | 01030A
1 | 108-1 |  | 01031A |  |  |  | Out |  |  |  |  | YES | YES |  |  | 1
1 | 108-1 | 12051 | 01032A
1 | 101A |  | 01033
1 | 101 | 27527 | 01034
1 | 110 | 12007
2 | 201-0 |  | 02001A
2 | 201-0 | 12073 | 02002A
2 | 201-1 |  | 02003A
2 | 201-2 |  | 02004A
2 | 202-0 |  | 02005A
2 | 202-0 | 12052 | 02006A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1 | 1 | 1 | 1 |  | 1 |  | 1
2 | 202-0 |  | 02007A
2 | 202-1 |  | 02008A
2 | 202-2 |  | 02009A
2 | 203-0 |  | 02010A
2 | 203-0 |  | 02011A
2 | 203-0 | 12074 | 02012A
2 | 203-1 |  | 02013A
2 | 203-2 |  | 02014A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1 | 1 | 1 | 1 |  | 1
2 | 204-0 | 12053 | 02015A
2 | 204-0 |  | 02016A
2 | 204-1 |  | 02017A
2 | 204-2 |  | 02018A
2 | 205-0 | 12269 | 02019A
2 | 205-0 |  | 02020A
2 | 205-1 |  | 02021A
2 | 205-2 |  | 02022A
2 | 206-0 | 12069 | 02023A
2 | 206-0 |  | 02024A
2 | 206-0 |  | 02025A
2 | 206-1 |  | 02026A
2 | 206-2 |  | 02027A
2 | 206-3 |  | 02028A
2 | 207-0 |  | 02029A
2 | 207-0 | 12060 | 02030A | [7 empty] | Phone wire stuck in phone jack
2 | 207-0 |  | 02031A
2 | 207-1 |  | 02032A
2 | 207-2 |  | 02033A
2 | 207-3 |  | 02034A
2 | 208-0 |  | 02035A
2 | 208-0 | 12054 | 02036A |  |  |  | In |  |  |  |  | YES | YES | [6 empty] | 1
2 | 208-1 |  | 02037A
2 | 208-2 |  | 02038A |  |  |  | Out |  |  |  |  | YES | YES |  |  | 1 | 1 | 1 | 1 |  |  |  | 1
2 | LOBBY |  | 02039A
2 | LOBBY |  | 02040A
3 | 301-0 |  | 03001A
3 | 301-0 | 12084 | 03002A
3 | 301-1 |  | 03003A
3 | 301-2 |  | 03004A
3 | 302-0 |  | 03005A
3 | 302-0 | 12061 | 03006A
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03008A
3 | 302-2 |  | 03009A
3 | 303-0 | 12088 | 03010A |  |  |  | In |  | No Cxn |  |  | YES | YES |  |  | 1 | [6 empty] | 1
3 | 303-0 |  | 03011A | [5 empty] | No Cxn |  |  | YES | YES
3 | 303-0 |  | 03012A
3 | 303-1 |  | 03013A
3 | 303-2 |  | 03014A
3 | 304-0 | 12070 | 03015A
3 | 304-0 |  | 03016A
3 | 304-1 |  | 03017A
3 | 304-2 |  | 03018A
3 | 305-0 | 12095 | 03019A
3 | 305-0 |  | 03020A
3 | 305-1 |  | 03021A |  |  |  | Out |  |  |  |  | YES | YES | [6 empty] | 1
3 | 305-2 |  | 03022A
3 | 306-0 | 12085 | 03023A
3 | 306-0 |  | 03024A
3 | 306-0 |  | 03025A
3 | 306-1 |  | 03026A
3 | 306-2 |  | 03027A
3 | 306-3 |  | 03028A
3 | 307-0 | 12075 | 03029A |  |  |  | No Cxn |  |  |  |  | YES | YES
3 | 307-0 |  | 03030A
3 | 307-0 |  | 03031A
3 | 307-1 |  | 03032A
3 | 307-2 |  | 03033A
3 | 307-3 |  | 03034A |  |  |  | Out |  |  |  |  | YES | YES |  |  | 1 | 1 | 1 | 1 |  | 1
3 | 308-0 |  | 03035A
3 | 308-0 | 12085 | 03036A | [7 empty] | Extension is incorrect
3 | 308-1 |  | 03037A
3 | 308-2 |  | 03038A
|  |  |  | 0 | 0 | 0 | 10 | 0 | 4 | 1 |  | 13 | 14 | 0 | 0 | 7 | 5 | 5 | 5 | 3 | 4 | 0 | 4 | 0
|  |  | No Cxn |  |  |  | 1 | 0 | 3
|  |  | Stuck |  |  |  | 0 | 0 | 0
|  |  | In | 0 |  |  | 5 | 1 | 1
|  |  | Out | 0 |  |  | 4 | 0 | 0
|  |  | Replaced | [6 empty] | 0
|  |  | Loose | 0 | 0 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 1
|  |  | Broken |  | 0 |  |  |  |  | 0
Note on J88: Eric Carpenter July 12 2017 Dial tone is on 03010A

## Delancey (CB)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 101-0 | 12089 | 01001A | [7 empty] | Locked
1 | 101-0 |  | 01002A | [7 empty] | Locked
1 | 101-1 | 23276 | 01002A | [7 empty] | Locked
1 | 102-0 |  | 01003A |  |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
1 | 102-1 |  | 01004A
1 | 102-2 |  | 01005A
1 | 102-0 |  | 01006A
1 | 103-0 |  | 01007A | [7 empty] | Video short
1 | 102-0 | 12089 | 01001A |  | Broken |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  | 1 |  | 1
1 | 103-0 |  | 01006A
1 | 103-0 | 12330 | 01008A | Loose |  |  | In
1 | 103-1 |  | 01009A
1 | 103-2 |  | 01010A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 104-0 | 12096 | 01011A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 104-0 |  | 01012A | Loose | [7 empty] | YES | YES | 1
1 | 104-1 |  | 01013A | Loose | [7 empty] | YES | YES | 1 |  |  |  |  | 1
1 | 104-2 |  | 01014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 105-0 | 12086 | 01015A | [7 empty] | Video short
1 | 105-0 |  | 01016A | [7 empty] | Video short
1 | 105-1 |  | 01017A | [7 empty] | Video short
1 | 105-2 |  | 01018A | [7 empty] | Video short
1 | 106-0 | 12063 | 01019A | [7 empty] | Video short
1 | 106-0 |  | 01020A | Loose | [6 empty] | Video short | YES | YES | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
1 | 106-0 |  | 01021A | [7 empty] | Video short
1 | 106-1 |  | 01022A | [7 empty] | Video short
1 | 106-2 |  | 01023A |  |  |  | In |  |  |  |  | YES | YES | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
1 | 106-3 |  | 01024A | [7 empty] | Video short
1 | 107-0 |  | 01025A |  |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
1 | 107-0 | 12055 | 01026A | [5 empty] | No Cxn |  |  | YES | YES | [7 empty] | 1
1 | 107-0 |  | 01027A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
1 | 107-1 |  | 01028A
1 | 107-2 |  | 01029A
1 | 107-3 |  | 01030A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
1 | 108-1 |  | 01031A | [7 empty] | Video short
1 | 108-1 | 12097 | 01032A
2 | LOUNGE1 201 - 204 |  | 02040A | Out | [6 empty] | Video short | YES | YES | 1
2 | 201-0 |  | 02001A | [7 empty] | Video short
2 | 201-0 | 12064 | 02002A
2 | 201-1 |  | 02003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 201-2 |  | 02004A
2 | 202-0 |  | 02005A | Out |  |  | In |  |  |  |  | YES | YES | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
2 | 202-0 |  | 02006A | [7 empty] | Video short
2 | 202-0 | 12291 | 02007A | Loose | [6 empty] | Video short | YES | YES | 1
2 | 202-1 |  | 02008A
2 | 202-2 |  | 02009A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 203-0 | 12065 | 02010A
2 | 203-0 |  | 02011A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
2 | 203-0 |  | 02012A
2 | 203-1 |  | 02013A | Out | [7 empty] | YES | YES |  | 1
2 | 203-2 |  | 02014A
2 | 204-0 | 12098 | 02015A | [7 empty] | Video short
2 | 204-0 |  | 02016A | [7 empty] | Video short
2 | 204-1 |  | 02017A
2 | 204-2 |  | 02018A
2 | LOUNGE2 205 - 208 |  | 0203A
2 | 205-0 | 12076 | 02019A
2 | 205-0 |  | 02020A
2 | 205-1 |  | 02022A
2 | 205-2 |  | 02021A
2 | 206-0 |  | 02023A | [7 empty] | Video short
2 | 206-0 | 12066 | 02024A | [7 empty] | Video short
2 | 206-0 |  | 02025A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 206-1 |  | 02026A
2 | 206-2 |  | 02027A
2 | 206-3 |  | 02028A
2 | 207-0 |  | 02029A
2 | 207-0 |  | 02030A
2 | 207-0 | 12285 | 02031A
2 | 207-1 |  | 02032A
2 | 207-2 |  | 02033A
2 | 207-3 |  | 02034A |  |  |  | Out | Out |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
2 | 208-0 |  | 02035A
2 | 208-0 | 12090 | 02036A
2 | 208-1 |  | 02037A |  |  |  | Out |  |  |  |  | YES | YES | [5 empty] | 1
2 | 208-2 |  | 02038A
2 | LOBBY |  | 02039A
2 | LOBBY |  | 02040A
3 | 301-0 |  | 03001A
3 | 301-0 | 12077 | 03002A | Loose | [7 empty] | YES | YES | 1
3 | 301-1 |  | 03003A |  |  |  | In |  |  |  | Video short | YES | YES | [5 empty] | 1
3 | 301-2 |  | 03004A
3 | 302-0 | 12099 | 03005A |  | Loose |  | Out | Out | Out |  | Phone jacks dead | YES | YES | [5 empty] | 1
3 | 302-0 |  | 03006A
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03008A | [7 empty] | Video short
3 | 302-2 |  | 03009A
3 | 303-0 |  | 03010A
3 | 303-0 |  | 03011A
3 | 303-0 | 12319 | 03012A
3 | 303-1 |  | 03013A
3 | 303-2 |  | 03014A
3 | 304-0 | 12056 | 03015A | [7 empty] | Video short
3 | 304-0 |  | 03016A | [5 empty] | In |  | Video short | YES | YES | [5 empty] | 1
3 | 304-1 |  | 03017A
3 | 304-2 |  | 03018A
3 | 305-0 | 12091 | 03019A
3 | 305-0 |  | 03020A
3 | 305-1 |  | 03021A | [7 empty] | Video short
3 | 305-2 |  | 03022A
3 | 306-0 |  | 03023A
3 | 306-0 | 12078 | 03024A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 306-0 |  | 03025A
3 | 306-1 |  | 03026A
3 | 306-2 |  | 03027A | [7 empty] | Video short
3 | 306-3 |  | 03028A
3 | 307-0 |  | 03029A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 307-0 | 12067 | 03030A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 307-0 |  | 03031A | Out | [7 empty] | YES | YES | 1
3 | 307-1 |  | 03032A
3 | 307-2 |  | 03033A
3 | 307-3 |  | 03034A
3 | 308-0 |  | 03035A | Loose | [7 empty] | YES | YES | 1
3 | 308-0 | 12057 | 03036A
3 | 308-1 |  | 03037A
3 | 308-2 |  | 03038A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
| 115 |  |  | 11 | 2 | 0 | 22 | 4 | 3 | 0 |  | 21 | 21 | 12 | 7 | 6 | 6 | 6 | 19 | 1 | 1 | 6 | 0 | 0
|  |  | No Cxn |  |  |  | 0 | 0 | 1
|  |  | In | 0 |  |  | 19 | 1 | 1
|  |  | Out | 4 |  |  | 3 | 2 | 1
|  |  | Replaced | [6 empty] | 0
|  |  | Loose | 7 | 1 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 1 |  |  |  |  | 0
Note on B9: Eric Carpenter June 12 17 used to be 102-0 changed to 103-0
Note on C10: Eric Carpenter June 12 17 Used to be 12330 Changed to 12089
Note on D10: Eric Carpenter June 12 17 Need to check this duplicate jacks exist
Note on D11: Eric Carpenter June 12 17 This needs to be checked. Duplicate jacks were found here

## Hamilton (CC)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 0101-1 | 24096 | j.01007
1 | 0101-1 | 24096 | j.01008
1 | 0101-1 |  | j.01001
1 | 0101-1 |  | j.01002
1 | 0101-3 | 24096 | j.01003
1 | 0101-3 | 24096 | j.01004
1 | 0101-4 | 24096 | j.01005
1 | 0101-4 | 12009 | j.01006
1 | 102-0 |  | 01043A
1 | 102-0 |  | 01044A
1 | 102-0 | 12104 | 01056A
1 | 102-1 |  | 01045A
1 | 102-1 |  | 01046A
1 | 102-2 |  | 01047A |  |  |  | In |  |  |  |  | YES | YES
1 | 102-3 |  | 01048A |  |  |  | In |  |  |  |  | YES | YES
1 | 102-3 |  | 01049A |  |  |  | In | In |  |  |  | YES | YES
1 | 102-3 |  | 01050A
1 | 104-0 |  | 01037A
1 | 104-0 |  | 01038A
1 | 104-0 | 12302 | 01055A
1 | 104-1 |  | 01039A
1 | 104-1 |  | 01040A
1 | 104-2 |  | 01041A
1 | 104-2 |  | 01042A
1 | 106-0 |  | 01031A
1 | 106-0 |  | 01032A
1 | 106-0 | 12048 | 01054A
1 | 106-1 |  | 01033A |  |  |  | In |  |  |  |  | YES | YES
1 | 106-1 |  | 01034A |  |  |  | In |  |  |  |  | YES | YES
1 | 106-2 |  | 01035A
1 | 106-2 |  | 01036A
1 | 107-0 |  | 01018A
1 | 107-0 |  | 01019A
1 | 107-0 | 12263 | 01052A | [6 empty] | Missing |  |  | YES
1 | 107-1 |  | 01015A |  |  |  | In |  |  |  |  | YES | YES
1 | 107-1 |  | 01016A
1 | 107-2 |  | 01017A
1 | 107-3 |  | 01020A
1 | 107-3 |  | 01021A |  |  |  |  | In | In |  |  | YES | YES
1 | 107-3 |  | 01022A
1 | 108-0 |  | 01023A
1 | 108-0 |  | 01024A
1 | 108-0 | 12045 | 01053A
1 | 108-1 |  | 01025A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
1 | 108-1 |  | 01026A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
1 | 108-1 |  | 01027A
1 | 108-2 |  | 01028A
1 | 108-3 |  | 01029A |  |  |  | Out |  |  |  |  | YES | YES |  |  | 1
1 | 108-3 |  | 01030A |  |  |  | In |  |  |  | 108-3 (no fourth room) | YES | YES | [5 empty] | 1
2 | 201-0 |  | 02001A
2 | 201-0 |  | 02004A
2 | 201-0 | 12303 | 02060A
2 | 201-1 |  | 02002A
2 | 201-1 |  | 02003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 201-1 |  | 02068A
2 | 201-2 |  | 02005A
2 | 201-3 |  | 02006A |  |  |  | In |  |  |  |  | YES | YES
2 | 201-3 |  | 02007A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 202-0 |  | 02052A
2 | 202-0 |  | 02053A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 202-0 | 12265 | 02067A
2 | 202-1 |  | 02054A
2 | 202-1 |  | 02055A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 202-2 |  | 02056A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 202-3 |  | 02057A
2 | 202-3 |  | 02058A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 202-3 |  | 02059A
2 | 203-0 |  | 02008A
2 | 203-0 |  | 02009A
2 | 203-0 | 12101 | 02061A
2 | 203-1 |  | 02010A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 203-1 |  | 02011A
2 | 203-2 |  | 02012A
2 | 204-0 |  | 02045A
2 | 204-0 |  | 02046A
2 | 204-0 | 12100 | 02066A
2 | 204-1 |  | 02047A
2 | 204-1 |  | 02048A
2 | 204-2 |  | 02049A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
2 | 204-3 |  | 02050A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
2 | 204-3 |  | 02051A
2 | 205-0 |  | 02013A | [7 empty] | lounge
2 | 205-0 |  | 02014A | [7 empty] | lounge
2 | 206-0 |  | 02036A
2 | 206-0 |  | 02037A
2 | 206-0 | 12050 | 02065A
2 | 206-1 |  | 02038A
2 | 206-1 |  | 02039A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 206-2 |  | 02040A
2 | 206-3 |  | 02041A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 206-3 |  | 02042A
2 | 207-0 |  | 02015A
2 | 207-0 |  | 02016A
2 | 207-0 | 12300 | 02062A
2 | 207-1 |  | 02017A
2 | 207-2 |  | 02018A
2 | 207-2 |  | 02019A
2 | 208-0 |  | 02028A
2 | 208-0 |  | 02029A |  |  |  | In |  |  |  |  | YES | YES |  | 1
2 | 208-0 | 12262 | 02064A
2 | 208-1 |  | 02030A
2 | 208-1 |  | 02031A
2 | 208-1 |  | 02032A
2 | 208-2 |  | 02033A
2 | 208-3 |  | 02034A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 208-3 |  | 02035A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
2 | 209-0 |  | 02020A
2 | 209-0 |  | 02021A |  |  |  | In |  |  |  |  | YES | YES |  | 1
2 | 209-0 | 12046 | 02063A
2 | 209-1 |  | 02022A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 209-1 |  | 02023A
2 | 209-2 |  | 02024A
2 | 209-3 |  | 02025A |  |  |  | In | In |  |  |  | YES | YES |  | 1
2 | 209-3 |  | 02026A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 209-3 |  | 02027A
3 | 301-0 |  | 03060A
3 | 301-0 |  | 03001A
3 | 301-0 | 12260 | 03061A
3 | 301-1 |  | 03002A
3 | 301-1 |  | 03003A
3 | 301-1 |  | 03004A
3 | 301-2 |  | 03005A
3 | 301-3 |  | 03006A |  |  |  |  | In |  |  |  | YES | YES |  |  |  | 1
3 | 301-3 |  | 03007A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
3 | 302-0 |  | 03050A
3 | 302-0 |  | 03051A
3 | 302-0 | 12047 | 03068A
3 | 302-1 |  | 03052A
3 | 302-1 |  | 03053A
3 | 302-2 |  | 03054A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 302-3 |  | 03055A
3 | 302-3 |  | 03056A
3 | 302-3 |  | 03057A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
3 | 303-0 |  | 03008A
3 | 303-0 |  | 03009A
3 | 303-0 | 12301 | 03062A
3 | 303-1 |  | 03010A
3 | 303-1 |  | 03011A
3 | 303-2 |  | 03012A
3 | 304-0 |  | 03043A
3 | 304-0 |  | 03044A
3 | 304-0 | 12049 | 03067A
3 | 304-1 |  | 03045A
3 | 304-1 |  | 03046A |  |  |  | In | In |  |  |  | YES | YES |  | 1
3 | 304-2 |  | 03047A
3 | 304-3 |  | 03048A
3 | 304-3 |  | 03049A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 305-0 |  | 03013A | [7 empty] | lounge
3 | 305-0 |  | 03014A | [7 empty] | lounge
3 | 306-0 |  | 03036A
3 | 306-0 |  | 03037A |  |  |  | In |  |  |  |  | YES | YES |  | 1
3 | 306-0 | 12261 | 03066A
3 | 306-1 |  | 03038A
3 | 306-1 |  | 03039A
3 | 306-2 |  | 03040A
3 | 306-3 |  | 03041A
3 | 306-3 |  | 03042A
3 | 307-0 |  | 03015A
3 | 307-0 |  | 03016A
3 | 307-0 | 12102 | 03063A
3 | 307-1 |  | 03017A
3 | 307-2 |  | 03018A
3 | 307-2 |  | 03019A
3 | 308-0 |  | 03028A
3 | 308-0 |  | 03029A
3 | 308-0 | 12103 | 03065A
3 | 308-1 |  | 03030A
3 | 308-1 |  | 03031A
3 | 308-1 |  | 03032A
3 | 308-2 |  | 03033A
3 | 308-3 |  | 03034A
3 | 308-3 |  | 03035A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 309-0 |  | 03020A
3 | 309-0 |  | 03021A | [9 empty] | 39 | 0 | 13 | 14 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 0
3 | 309-0 | 12304 | 03064A
3 | 309-1 |  | 03022A
3 | 309-1 |  | 03023A
3 | 309-2 |  | 03024A
3 | 309-3 |  | 03025A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
3 | 309-3 |  | 03026A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
3 | 309-3 |  | 03027A
173 |  |  |  | 0 | 0 | 0 | 37 | 6 | 1 | 1 |  | 40
|  |  | No Cxn |  |  |  | 0 | 0 | 0
|  |  | In | 0 |  |  | 36 | 1 | 1
|  |  | Out | 0 |  |  | 1 | 0 | 0
|  |  | Replaced | [6 empty] | 0
|  |  | Loose | 0 | 0 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 1
|  |  | Broken |  | 0 |  |  |  |  | 0
RD
OF
1 | 103 | 27529 | j.01011
1 | 103 |  | j.01012
1 | NA |  | j.01013
1 | NA |  | j.01014
NF
0 | B01 |  | j.00017
0 | B02 |  | j.00018
0 | B04 | 12305 | j.00019
0 | B04 |  | j.00020
0 | B04 |  | j.00021
0 | B04 |  | j.00022
0 | B06 |  | j.00001
0 | B06 |  | j.00002
0 | B06 |  | j.00023
0 | B06 |  | j.00025
0 | B08 | 12264 | j.00003
0 | B08 |  | j.00004
0 | B08 |  | j.00005
0 | B08 |  | j.00006
0 | B09 |  | j.00009
0 | B09 |  | j00010
0 | B09 |  | j.00011
0 | B09 |  | j.00012
0 | B09 |  | j.00013
0 | B09 |  | j.00014
0 | B10 |  | j.00024
0 | B10 |  | j.00007
0 | B10 |  | j.00008
0 | NA |  | j.00015
0 | NA |  | j.00016
1 | 100-A |  | j.01057
1 | 100 |  | j.01009
1 | 100 |  | j.01010
1 | 100 |  | j.01058
1 | 100 |  | j.01059
2 | 02EC1 |  | j.02043
2 | 02EC1 |  | j.02044
2 | 0200C1 |  | j.02069
3 | 03EC1 |  | j.03058
3 | 03EC1 |  | j.03059
3 | 0300C1 |  | j.03069
Note on B83: Windows User: *not on res life list of rooms*

## Herkimer (CD)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 001 | 27528 | 00001A
1 | 110-0 | 12010
1 | 103-0 | 12092 | 01002A
1 | 103-0 |  | 01003A
1 | 103-0 |  | 01004A
1 | 103-1 |  | 01005A
1 | 103-2 |  | 01006A
1 | 103-3 |  | 01007A
1 | 104-0 | 12079 | 01008A
1 | 104-0 |  | 01009A
1 | 104-1 |  | 01010A
1 | 104-2 |  | 01011A
1 | 105-0 | 12058 | 01012A
1 | 105-0 |  | 01013A
1 | 105-1 |  | 01014A
1 | 105-2 |  | 01015A
1 | 106-0 |  | 01016A
1 | 106-0 | 12105 | 01017A
1 | 106-0 |  | 01018A
1 | 106-1 |  | 01019A
1 | 106-2 |  | 01020A
1 | 106-3 |  | 01021A
1 | 107-0 | 12080 | 01022A
1 | 107-0 |  | 01023A
1 | 107-0 |  | 01024A
1 | 107-1 |  | 01025A
1 | 107-2 |  | 01026A
1 | 107-3 |  | 01027A
1 | 108-1 |  | 01028A
1 | 108-1 | 12081 | 01029A
2 | 201-0 |  | 02001A
2 | 201-0 | 12093 | 02002A
2 | 201-1 |  | 02003A
2 | 201-2 |  | 02004A
2 | 202-0 |  | 02005A
2 | 202-0 | 12071 | 02006A
2 | 202-0 |  | 02007A
2 | 202-1 |  | 02008A
2 | 202-2 |  | 02009A
2 | 202-3 |  | 02010A
2 | 203-0 | 12106 | 02011A
2 | 203-0 |  | 02012A
2 | 203-0 |  | 02013A
2 | 203-1 |  | 02014A
2 | 203-2 |  | 02015A
2 | 203-3 |  | 02016A
2 | 204-0 | 12094 | 02017A
2 | 204-0 |  | 02018A
2 | 204-1 |  | 02019A
2 | 204-2 |  | 02020A
2 | 205-0 | 12082 | 02021A
2 | 205-0 |  | 02022A
2 | 205-1 |  | 02023A
2 | 205-2 |  | 02024A
2 | 206-0 |  | 02025A
2 | 206-0 | 12134 | 02026A
2 | 206-0 |  | 02027A
2 | 206-1 |  | 02028A
2 | 206-2 |  | 02029A
2 | 206-3 |  | 02030A
2 | 207-0 | 12185 | 02031A
2 | 207-0 |  | 02032A
2 | 207-0 |  | 02033A
2 | 207-1 |  | 02034A
2 | 207-2 |  | 02035A
2 | 207-3 |  | 02036A
2 | 208-0 | 12166 | 02037A
2 | 208-0 |  | 02038A
2 | 208-1 |  | 02039A
2 | 208-2 |  | 02040A
3 | 301-0 |  | 03001A
3 | 301-0 | 12140 | 03002A
3 | 301-1 |  | 03003A
3 | 301-2 |  | 03004A
3 | 302-0 | 12186 | 03005A
3 | 302-0 |  | 03006A
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03008A
3 | 302-2 |  | 03009A
3 | 302-3 |  | 03010A
3 | 303-0 | 12155 | 03011A
3 | 303-0 |  | 03012A
3 | 303-0 |  | 03013A
3 | 303-1 |  | 03014A
3 | 303-2 |  | 03015A
3 | 303-3 |  | 03016A
3 | 304-0 | 12141 | 03017A
3 | 304-0 |  | 03018A
3 | 304-1 |  | 03019A
3 | 304-2 |  | 03020A
3 | 305-0 | 12107 | 03021A
3 | 305-0 |  | 03022A
3 | 305-1 |  | 03023A
3 | 305-2 |  | 03024A
3 | 306-0 |  | 03025A
3 | 306-0 | 12167 | 03026A
3 | 306-0 |  | 03027A
3 | 306-1 |  | 03028A
3 | 306-2 |  | 03029A
3 | 306-3 |  | 03030A
3 | 307-0 | 12142 | 03031A
3 | 307-0 |  | 03032A
3 | 307-0 |  | 03033A
3 | 307-1 |  | 03034A
3 | 307-2 |  | 03035A
3 | 307-3 |  | 03036A
3 | 308-0 |  | 03037A
3 | 308-0 | 12135 | 03038A
3 | 308-1 |  | 03039A
3 | 308-2 |  | 03040A
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | No Cxn |  |  |  | 0 | 0 | 0
|  |  | Stuck |  |  |  | 0 | 0 | 0
|  |  | In | 0 |  |  | 0 | 0 | 0
|  |  | Out | 0 |  |  | 0 | 0 | 0
|  |  | Replaced | [6 empty] | 0
|  |  | Loose | 0 | 0 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 0 |  |  |  |  | 0
RD
1 | CD01020 |  | 01003A
1 | CD01021 | 23276 | 00101A

## Johnson (CE)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 102-0 |  | 01005A
1 | 102-0 |  | 01006A
1 | 102-1 |  | 01007A
1 | 102-1 | 12187 | 01008A
1 | 102-2 | 12130 | 01009A
1 | 102-2 |  | 01010A |  |  |  | No Cxn |  |  |  |  | YES | YES
1 | 104-0 |  | 01011A
1 | 104-0 |  | 01012A
1 | 104-1 |  | 01013A
1 | 104-1 | 12171 | 01014A
1 | 104-2 |  | 01014A
1 | 104-2 | 12188 | 01015A
1 | 104-2 |  | 01016A
1 | 105-0 |  | 01019A
1 | 105-0 |  | 01020A
1 | 105-0 |  | 01021A
1 | 105-1 | 12144 | 01022A
1 | 105-1 |  | 01023A
1 | 105-2 | 12172 | 01024A
1 | 105-2 |  | 01025A
1 | 106-0 |  | 01030A
1 | 106-0 |  | 01031A
1 | 106-0 |  | 01030A
1 | 106-1 |  | 01033A
1 | 106-1 | 12331 | 01034A |  |  |  | No Cxn |  |  |  |  | YES | YES
1 | 106-2 |  | 01035A
1 | 106-2 | 12170 | 01036A
1 | 106-3 |  | 01037A
1 | 106-3 | 12143 | 01038A
1 | 107-0 |  | 01039A
1 | 107-0 |  | 01049A
1 | 107-0 |  | 01041A |  |  |  | In |  |  |  |  | YES | YES
1 | 107-1 |  | 01042A
1 | 107-1 | 12110 | 01043A
1 | 107-2 |  | 01044A |  | Loose | [6 empty] | YES | YES | [10 empty] | 1
1 | 107-2 | 12335 | 01045A
1 | 107-3 |  | 01028A
1 | 107-3 | 12334 | 01029A
1 | 108-0 | 12168 | 01026A
1 | 108-0 |  | 01027A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
2 | LOUNGE1 201 - 204 |  | 2051
2 | 201-0 |  | 2019A
2 | 201-0 |  | 02020A
2 | 201-1 |  | 02021A
2 | 201-1 | 12174 | 02022A
2 | 201-2 | 12124 | 02023A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 201-2 |  | 02024A
2 | 202-0 |  | 02007A
2 | 202-0 |  | 02008A
2 | 202-1 |  | 02009A
2 | 202-1 | 12189 | 02010A
2 | 202-2 | 12309 | 02011A
2 | 202-2 |  | 02012A
3 | 203-0 |  | 02001A
3 | 203-0 |  | 02002A
2 | 203-1 |  | 02003A
2 | 203-1 | 12156 | 02004A
2 | 203-2 | 12112 | 02005A
2 | 203-2 |  | 02006A
2 | 204-0 |  | 02013A
2 | 204-0 |  | 02014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 204-1 |  | 02015A
2 | 204-1 | 12320 | 02016A
2 | 204-2 | 12190 | 02017A
2 | 204-2 |  | 02018A
2 | LOUNGE2 205 - 208 |  | 2052
2 | 205-0 |  | 02025A
2 | 205-0 |  | 02025A
2 | 205-1 |  | 02027A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 205-1 | 12192 | 02028A
2 | 205-2 | 12113 | 02029A
2 | 205-2 |  | 02030A
2 | 206-0 |  | 02037A
2 | 206-0 |  | 02038A
2 | 206-1 | 12173 | 02039A
2 | 206-2 |  | 02040A
2 | 206-2 | 12123 | 02041A
2 | 206-3 |  | 02042A
2 | 206-3 | 12191 | 02043A
2 | 207-0 |  | 02044A
2 | 207-0 |  | 02045A
2 | 207-1 |  | 02046A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 207-1 | 12145 | 02047A
2 | 207-2 |  | 02048A
2 | 207-2 | 12175 | 02049A
2 | 207-3 | 12125 | 02050A
2 | 208-0 |  | 02031A
2 | 208-0 |  | 02032A
2 | 208-1 |  | 02033A
2 | 208-1 | 12193 | 02034A
2 | 208-2 | 12111 | 02035A
2 | 208-2 |  | 02036A
3 | 301-0 |  | 03019A
3 | 301-0 |  | 03020A
3 | 301-1 |  | 03021A
3 | 301-1 | 12136 | 03022A
3 | 301-2 | 12146 | 03023A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 301-2 |  | 03024A
3 | 302-0 |  | 03007A
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03009A
3 | 302-1 | 12115 | 03010A
3 | 302-2 | 12147 | 03011A
3 | 302-2 |  | 03012A
3 | 303-0 |  | 03001A
3 | 303-0 |  | 03002A
3 | 303-1 |  | 03003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 303-1 | 12176 | 03004A
3 | 303-2 | 12126 | 03005A
3 | 303-2 |  | 03006A
3 | 304-0 |  | 03013A
3 | 304-0 |  | 03014A
3 | 304-1 |  | 03015A
3 | 304-1 | 12128 | 03016A
3 | 304-2 | 12177 | 03017A
3 | 304-2 |  | 03018A
3 | 305-0 |  | 03025A
3 | 305-0 |  | 03026A |  |  |  | No Cxn |  |  |  |  | YES | YES
3 | 305-1 |  | 03027A
3 | 305-1 | 12295 | 03028A
3 | 305-2 | 12157 | 03029A
3 | 305-2 |  | 03030A
3 | 306-0 |  | 03037A |  |  |  | In |  |  |  |  | YES | YES
3 | 306-0 |  | 03038A
3 | 306-1 | 12194 | 03039A
3 | 306-2 |  | 03040A
3 | 306-2 | 12158 | 03041A
3 | 306-3 |  | 03042A
3 | 306-3 | 12129 | 03043A
3 | 307-0 |  | 03044A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
3 | 307-0 |  | 03045A
3 | 307-1 |  | 03046A
3 | 307-1 | 12289 | 03047A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1 |  |  |  |  | 1
3 | 307-2 |  | 03048A
3 | 307-2 | 12116 | 03049A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 307-3 | 12148 | 03050A
3 | 308-0 |  | 03031A
3 | 308-0 |  | 03032A
3 | 308-1 |  | 03033A |  | Loose | [6 empty] | YES | YES | [10 empty] | 1
3 | 308-1 | 12127 | 03034A
3 | 308-2 | 12137 | 03035A
3 | 308-2 |  | 03036A
142 |  |  |  | 0 | 2 | 0 | 14 | 1 | 0 | 0 |  | 17 | 17 | 0 | 0 | 1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 3
|  |  | No Connection |  |  |  | 3 | 0 | 0
|  |  | In | 0 |  |  | 11 | 1 | 0
|  |  | Out | 0 |  |  | 0 | 0 | 0
|  |  | Replaced | [6 empty] | 0
|  |  | Loose | 0 | 2 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 0 |  |  |  |  | 0
RD
1 | CE01030 | 25392 | 01001A
1 | CE01031 | 12122 | 01003A
1 | CE01032 | 12169 | 01004A
NF
1 | CEO1100 | 12011
1 | CEO1101 | 12023
1 | CEO1102 | 27522 | 01018A
2 | LOBBY |  | 02039A
2 | LOBBY |  | 02040A
3 | CE01010 |  | 5IC102
1 | STUDY |  | 00001A
1 | STUDY |  | 00002A
1 | CE00070 |  | 00003A
1 | CE00070 |  | 00004A
1 | CE00070 | 27525 | 00005A
1 | STUDY |  | 00006A
1 | CE0016 | 12114 | 00012A
1 | CE01010 | 12109 | 01017A
Note on B33: Eric Carpenter July 12 2017 Hoefller says there is no coax in the box

## Morris (CF)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 101-2 |  | 01012A | [7 empty] | Room locked
1 | 102-0 | 25917 | 01021A
1 | 110-0 | 12012
1 | 101-2 |  | 00101A
1 | 102-0 | 12159 | 01001A
1 | 102-0 |  | 01002A
1 | 102-0 |  | 01003A
1 | 102-1 |  | 01004A
1 | 102-2 |  | 01005A
1 | 103-0 |  | 01006A
1 | 103-0 | 12138 | 01007A
1 | 103-0 |  | 01008A
1 | 103-1 |  | 01009A
1 | 103-2 |  | 01010A
1 | 104-0 |  | 01011A
1 | 104-0 | 12195 | 01012A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  | 1 |  | 1
1 | 104-1 |  | 01013A
1 | 104-2 |  | 01014A
1 | 105-0 |  | 01015A
1 | 105-0 | 12160 | 01016A
1 | 105-1 |  | 01017A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 105-2 |  | 01018A | [7 empty] | video short
1 | 106-0 |  | 01019A | [7 empty] | video short
1 | 106-0 |  | 01020A
1 | 106-0 | 12332 | 01021A
1 | 106-1 |  | 01022A
1 | 106-2 |  | 01023A
1 | 106-3 |  | 01024A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 107-0 |  | 01025A
1 | 107-0 | 12196 | 01026A
1 | 107-0 |  | 01027A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 107-1 |  | 01028A
1 | 107-2 |  | 01029A
1 | 107-3 |  | 01030A
1 | 108-1 | 12161 | 01031A | [7 empty] | Room locked
1 | 108-1 |  | 01032A
2 | LOUNGE1 201 - 204 |  | 02-040
2 | 201-0 | 12197 | 02001A
2 | 201-0 |  | 02002A
2 | 201-1 |  | 02003A
2 | 201-2 |  | 02004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 202-0 | 12149 | 02005A | [7 empty] | video short
2 | 202-0 |  | 02006A
2 | 202-0 |  | 02007A | [7 empty] | video short
2 | 202-1 |  | 02008A
2 | 202-2 |  | 02009A | [7 empty] | video short
2 | 203-0 |  | 02010A
2 | 203-0 | 12131 | 02011A | [7 empty] | video short
2 | 203-0 |  | 02012A | [7 empty] | video short
2 | 203-1 |  | 02013A | [7 empty] | video short
2 | 203-2 |  | 02014A
2 | 204-0 |  | 02015A | [7 empty] | video short
2 | 204-0 | 12198 | 02016A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
2 | 204-1 |  | 02017A
2 | 204-2 |  | 02018A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
2 | LOUNGE2 205 - 208 |  | 02-039 | [7 empty] | video short
2 | 205-0 |  | 02019A
2 | 205-0 | 12150 | 02020A
2 | 205-1 |  | 02021A
2 | 205-2 |  | 02022A
2 | 206-0 |  | 02023A
2 | 206-0 |  | 02024A | [7 empty] | video short
2 | 206-0 | 12321 | 02025A
2 | 206-1 |  | 02026A
2 | 206-2 |  | 02027A
2 | 206-3 |  | 02028A
2 | 207-0 |  | 02029A
2 | 207-0 | 12199 | 02030A
2 | 207-0 |  | 02031A
2 | 207-1 |  | 02032A
2 | 207-2 |  | 02033A
2 | 207-3 |  | 02034A
2 | 208-0 |  | 02035A
2 | 208-0 | 12162 | 02036A
2 | 208-1 |  | 02037A
2 | 208-2 |  | 02038A | [7 empty] | video short
2 | LOBBY |  | 02039A
2 | LOBBY |  | 02040A
3 | 301-0 | 12117 | 03001A
3 | 301-0 |  | 03002A
3 | 301-1 |  | 03003A
3 | 301-2 |  | 03004A
3 | 302-0 | 12178 | 03005A | [7 empty] | Needs phone wire but phone works
3 | 302-0 |  | 03006A
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03008A
3 | 302-2 |  | 03009A
3 | 303-0 |  | 03010A
3 | 303-0 | 12151 | 03011A
3 | 303-0 |  | 03012A
3 | 303-1 |  | 03013A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 303-2 |  | 03014A
3 | 304-0 |  | 03015A
3 | 304-0 | 12118 | 03016A
3 | 304-1 |  | 03017A
3 | 304-2 |  | 03018A | [7 empty] | Video short
3 | 305-0 |  | 03019A
3 | 305-0 |  | 03022A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
3 | 305-0 | 12179 | 03020A
3 | 305-1 |  | 03021A
3 | 305-2 |  | 03022A
3 | 306-0 |  | 03023A | [7 empty] | Video short
3 | 306-0 |  | 03024A
3 | 306-0 | 12322 | 03025A
3 | 306-1 |  | 03026A
3 | 306-2 |  | 03027A
3 | 306-3 |  | 03028A
3 | 307-0 |  | 03029A
3 | 307-0 | 12119 | 03030A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
3 | 307-0 |  | 03031A
3 | 307-1 |  | 03032A
3 | 307-2 |  | 03033A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 307-3 |  | 03034A
3 | 308-0 | 12180 | 03035A
3 | 308-0 |  | 03036A
3 | 308-1 |  | 03037A
3 | 308-2 |  | 03038A
| 113 |  |  | 0 | 0 | 0 | 9 | 2 | 0 | 0 |  | 11 | 11 | 0 | 3 | 3 | 2 | 2 | 8 | 1 | 0 | 2 | 0 | 0
|  |  | No Connection |  |  |  | 0 | 0 | 0
|  |  | In | 0 |  |  | 9 | 0 | 0
|  |  | Out | 0 |  |  | 0 | 0 | 0
|  |  | Replaced | [6 empty] | 0
|  |  | Loose | 0 | 0 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 0 |  |  |  |  | 0

## Paine (CG)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 010 | 27523 | 00002A
1 | STUDY??? | 12139 | 01001A
1 | STUDY??? |  | 01002A
1 | 103-0 |  | 01003A
1 | 103-0 | 12283 | 01004A
1 | 103-1 |  | 01005A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
1 | 103-2 |  | 01006A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 103-3 |  | 01007A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
1 | 104-0 | 12152 | 01008A
1 | 104-0 |  | 01009A
1 | 104-1 |  | 01010A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
1 | 104-2 |  | 01011A
1 | 105-0 | 12120 | 01012A | [6 empty] | Replaced |  |  | YES
1 | 105-0 |  | 01013A
1 | 105-1 |  | 01014A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
1 | 105-2 |  | 01015A
1 | 106-0 |  | 01016A
1 | 106-0 |  | 01017A | Loose | [7 empty] | YES | YES | 1
1 | 106-0 | 12290 | 01018A | [6 empty] | Replaced |  |  | YES
1 | 106-1 |  | 01019A
1 | 106-2 |  | 01020A
1 | 107-0 |  | 01021A
1 | 107-0 | 12163 | 01022A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 107-1 |  | 01023A
1 | 107-2 |  | 01024A
1 | 108-1 | 12121 | 01025A
1 | 108-1 |  | 01026A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | LOUNGE1 201 - 204
2 | 201-0 |  | 02001A
2 | 201-0 | 12153 | 02002A | [6 empty] | Replaced |  |  | YES
2 | 201-1 |  | 02003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 201-2 |  | 02004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 202-0 | 12200 | 02005A
2 | 202-0 |  | 02006A
2 | 202-0 |  | 02007A
2 | 202-1 |  | 02008A
2 | 202-2 |  | 02009A
2 | 202-3 |  | 02010A
2 | 203-0 |  | 02011A
2 | 203-0 |  | 02012A
2 | 203-0 | 12310 | 02013A
2 | 203-1 |  | 02014A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
2 | 203-2 |  | 02015A
2 | 203-3 |  | 02016A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 204-0 | 12181 | 02017A
2 | 204-0 |  | 02018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 204-1 |  | 02019A
2 | 204-2 |  | 02020A
2 | LOUNGE2 205 - 208
2 | 205-0 | 12154 | 02021A
2 | 205-0 |  | 02022A | Loose | [7 empty] | YES | YES | 1
2 | 205-1 |  | 02023A
2 | 205-2 |  | 02024A
2 | 206-0 |  | 02025A
2 | 206-0 | 12132 | 02026A
2 | 206-0 |  | 02027A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 206-1 |  | 02028A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 206-2 |  | 02029A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 207-0 |  | 02030A
2 | 207-0 | 12182 | 02031A
2 | 207-0 |  | 02032A
2 | 207-1 |  | 02033A
2 | 207-2 |  | 02034A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 208-0 |  | 02035A
2 | 208-0 | 12183 | 02036A
2 | 208-1 |  | 02037A | Loose | [7 empty] | YES | YES | 1
2 | 208-2 |  | 02038A | Loose | [7 empty] | YES | YES | 1
2 | LOBBY |  | 02039A
2 | LOBBY |  | 02040A
3 | 301-0 |  | 03001A
3 | 301-0 | 12164 | 03002A
3 | 301-1 |  | 03004A
3 | 301-2 |  | 03003A
3 | 302-0 |  | 03005A
3 | 302-0 | 12201 | 03006A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03008A
3 | 302-2 |  | 03009A
3 | 302-3 |  | 03010A
3 | 303-0 | 12311 | 03011A | [5 empty] | No Cxn |  |  | YES | YES | [7 empty] | 1
3 | 303-0 |  | 03012A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 303-0 |  | 03013A
3 | 303-1 |  | 03014A
3 | 303-2 |  | 03015A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
3 | 303-3 |  | 03016A
3 | 304-0 | 12165 | 03017A
3 | 304-0 |  | 03018A
3 | 304-1 |  | 03019A
3 | 304-2 |  | 03020A
3 | 305-0 | 12133 | 03021A
3 | 305-0 |  | 03022A
3 | 305-1 |  | 03023A
3 | 305-2 |  | 03024A
3 | 306-0 |  | 03025A
3 | 306-0 |  | 03026A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 306-0 | 12323 | 03027A | Loose |  |  |  |  | In |  |  | YES | YES | 1
3 | 306-1 |  | 03028A
3 | 306-2 |  | 03029A
3 | 307-0 |  | 03030A
3 | 307-0 | 12184 | 03031A | Loose | [7 empty] | YES | YES | 1
3 | 307-0 |  | 03032A
3 | 307-1 |  | 03033A
3 | 307-2 |  | 03034A | Loose | [7 empty] | YES | YES | 1
3 | 308-0 |  | 03035A
3 | 308-0 | 12227 | 03036A
3 | 308-1 |  | 03037A | Out | [7 empty] | YES | YES | 1
3 | 308-1 |  | 03038A
107 |  |  |  | 8 | 0 | 0 | 19 | 2 | 2 | 3 |  | 29 | 32 | 8 | 4 | 4 | 3 | 3 | 16 | 0 | 1 | 3 | 0 | 0
|  |  | No Connection |  |  |  | 0 | 0 | 1
|  |  | In | 0 |  |  | 19 | 2 | 1
|  |  | Out | 1 |  |  | 0 | 0 | 0
|  |  | Replaced | [6 empty] | 3
|  |  | Loose | 7 | 0 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 0 |  |  |  |  | 0
RD
1 | CG01021 | 25917 | 01004A

## Zenger (CH)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 103-0 | 12202 | 01002A | Out | [7 empty] | YES | YES | 1
1 | 103-0 |  | 01003A
1 | 103-0 |  | 01004A
1 | 103-1 |  | 01005A |  |  |  | In |  |  |  |  | YES | YES |  | 1 |  |  |  | 1
1 | 103-2 |  | 01006A
1 | 103-3 |  | 01007A
1 | 104-0 | 12251 | 01008A
1 | 104-0 |  | 01009A
1 | 104-1 |  | 01010A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 104-2 |  | 01011A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
1 | 105-0 | 12228 | 01012A |  |  |  | Out |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
1 | 105-1 |  | 01013A
2 | LOUNGE1 201 - 204
2 | 201-0 |  | 02001A
2 | 201-0 | 12270 | 02002A
2 | 201-1 |  | 02003A
2 | 201-2 |  | 02004A
2 | 202-0 |  | 02005A
2 | 202-0 | 12229 | 02006A | [7 empty] | asbestos abatement
2 | 202-0 |  | 02007A
2 | 202-1 |  | 02008A
2 | 202-2 |  | 02009A
2 | 202-3 |  | 02010A
2 | 203-0 | 12203 | 02011A
2 | 203-0 |  | 02012A
2 | 203-0 |  | 02013A
2 | 203-1 |  | 02014A
2 | 203-2 |  | 02015A
2 | 203-3 |  | 02016A
2 | 204-0 | 12271 | 02017A
2 | 204-0 |  | 02018A
2 | 204-1 |  | 02019A
2 | 204-2 |  | 02020A
2 | 205-0 | 12230 | 02021A
2 | 205-0 |  | 02022A
2 | 205-1 |  | 02023A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 205-2 |  | 02024A
2 | 206-0 |  | 02025A
2 | 206-0 |  | 02026A
2 | 206-0 | 12333 | 02027A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 206-1 |  | 02028A
2 | 206-2 |  | 02029A
2 | 207-0 |  | 02030A |  |  |  | In |  |  |  |  | YES | YES |  | 1
2 | 207-0 |  | 02031A
2 | 207-0 | 12296 | 02032A
2 | 207-1 |  | 02033A
2 | 207-2 |  | 02034A
2 | 208-0 |  | 02035A
2 | 208-0 | 12231 | 02036A
2 | 208-1 |  | 02037A
2 | 208-2 |  | 02038A
2 | LOBBY |  | 02039A
2 | LOBBY |  | 02040A
3 | 301-0 |  | 03001A
3 | 301-0 | 12204 | 03002A
3 | 301-1 |  | 03003A
3 | 301-2 |  | 03004A
3 | 302-0 |  | 03005A | [7 empty] | above asbestos abatement
3 | 302-0 | 12252 | 03006A
3 | 302-0 |  | 03007A
3 | 302-1 |  | 03008A
3 | 302-2 |  | 03009A
3 | 302-3 |  | 03010A
3 | 303-0 | 12222 | 03011A | [6 empty] | Replaced |  |  | YES
3 | 303-0 |  | 03012A
3 | 303-0 |  | 03013A
3 | 303-1 |  | 03014A
3 | 303-2 |  | 03015A
3 | 303-3 |  | 03016A
3 | 304-0 | 12205 | 03017A
3 | 304-0 |  | 03018A
3 | 304-1 |  | 03019A
3 | 304-2 |  | 03020A
3 | 305-0 | 12253 | 03021A | Out | [7 empty] | YES | YES | 1
3 | 305-0 |  | 03022A | Loose | [7 empty] | YES | YES | 1
3 | 305-1 |  | 03023A
3 | 305-2 |  | 03024A
3 | 306-0 |  | 03025A
3 | 306-0 |  | 03026A
3 | 306-0 | 12284 | 03027A
3 | 306-1 |  | 03028A
3 | 306-2 |  | 03029A
3 | 307-0 | 12272 | 03030A | Out | [7 empty] | YES | YES | 1
3 | 307-0 |  | 03031A
3 | 307-0 |  | 03032A |  |  |  | In |  |  |  |  | YES | YES | 1
3 | 307-1 |  | 03033A
3 | 307-2 |  | 03034A
3 | 308-0 |  | 03035A
3 | 308-0 | 12254 | 03036A
3 | 308-1 |  | 03037A
3 | 308-2 |  | 03038A |  |  |  | In |  |  |  |  | YES | YES |  | 1
13 |  |  |  | 4 | 0 | 0 | 9 | 0 | 0 | 1 |  | 13 | 14 | 5 | 4 | 1 | 1 | 1 | 5 | 0 | 0 | 1 | 0 | 0
|  |  | No Connection |  |  |  | 0 | 0 | 0
|  |  | In | 0 |  |  | 8 | 0 | 0
|  |  | Out | 3 |  |  | 1 | 0 | 0
|  |  | Replaced | [6 empty] | 1
|  |  | Loose | 1 | 0 | 0
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 0 |  |  |  |  | 0
RD
1 | 102-0 |  | 01001A

## Livingston (CT)
Floor | Room | Extn | Jack | CABLE BOX | FACE-PLATE | WIRE-MOLD | VIDEO JACK | DATA JACK | PHONE JACK | RED PHONE | NOTES | TECH NEEDED | TECH-REDPHONE | RM BX | NFP | NFI | NDJ | NVJ | RI | DTG | DTNG | DLG | DLNG | RM FP
1 | 100 | 25915 | 01002A
1 | 104 | 25903 | 01003A
1 | 106 | 12030 | 01003A
1 | 101 |  | 01004A
1 | 106 | 12017 | 01004A
1 | 101 | 25599 | 01005A
1 | 106 | 25911 | 01005A
1 | 106 | 27526 | 01005B
2 | 0201-0 | 12232 | 02001A | [5 empty] | No Cxn |  |  | YES | YES | [9 empty] | 1
2 | 0201-0 |  | 02002A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 0201-1 |  | 02003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 0201-2 |  | 02004A
2 | 0202-0 |  | 02005A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 0202-0 | 12213 | 02006A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
2 | 0202-0 |  | 02007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 0202-1 |  | 02008A | [7 empty] | video short
2 | 0202-2 |  | 02009A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
2 | 0202-3 |  | 02010A
2 | 0203-0 | 12273 | 02011A |  |  |  | In |  |  | Replaced |  | YES | YES | [5 empty] | 1
2 | 0203-0 |  | 02012A
2 | 0203-0 |  | 02013A
2 | 0203-1 |  | 02014A
2 | 0203-2 |  | 02015A
2 | 0203-3 |  | 02016A
2 | 0204-0 | 12241 | 02017A
2 | 0204-0 |  | 02018A
2 | 0204-1 |  | 02019A
2 | 0204-2 |  | 02020A
2 | LOUNGE |  | 02021A | Loose | [7 empty] | YES | YES | 1 |  |  |  |  | 1
2 | LOBBY | 12000 | 02021C
2 | OUTSIDE | 12015 | 02021D
3 | 0301-0 | 12214 | 03001A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 0301-0 |  | 03002A
3 | 0301-0 |  | 03003A
3 | 0301-1 |  | 03004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 0301-2 |  | 03005A | Loose |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1 | [5 empty] | Wall broken
3 | 0301-3 |  | 03006A
3 | 0302-0 |  | 03007A | [7 empty] | video short
3 | 0302-0 | 12215 | 03008A
3 | 0302-0 |  | 03009A
3 | 0302-1 |  | 03010A
3 | 0302-2 |  | 03011A
3 | 0302-3 |  | 03012A
3 | 0303-0 | 12255 | 03013A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
3 | 0303-0 |  | 03014A
3 | 0303-0 |  | 03015A
3 | 0303-1 |  | 03016A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 0303-2 |  | 03017A
3 | 0303-3 |  | 03018A
3 | 0304-0 | 12242 | 03019A
3 | 0304-0 |  | 03020A
3 | 0304-0 |  | 03021A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 0304-1 |  | 03022A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 0304-2 |  | 03023A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
3 | 0304-3 |  | 03024A | [7 empty] | video short
4 | 0401-0 | 12224 | 04001A
4 | 0401-0 |  | 04002A
4 | 0401-1 |  | 04003A
4 | 0401-2 |  | 04004A | Loose |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
4 | 0402-0 |  | 04005A
4 | 0402-0 | 12206 | 04006A
4 | 0402-0 |  | 04007A
4 | 0402-1 |  | 04008A
4 | 0402-2 |  | 04009A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | [8 empty] | Note
4 | 0402-3 |  | 04010A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
4 | 0403-0 | 12256 | 04011A | [6 empty] | Replaced |  |  | YES
4 | 0403-0 |  | 04012A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
4 | 0403-0 |  | 04013A
4 | 0403-1 |  | 04014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
4 | 0403-2 |  | 04015A
4 | 0403-3 |  | 04016A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
4 | 0404-0 | 12233 | 04017A
4 | 0404-0 |  | 04018A
4 | 0404-1 |  | 04019A | [7 empty] | video short
4 | 0404-2 |  | 04020A
4 | LOUNGE |  | 04021A
5 | 0501-0 | 12207 | 05001A | [6 empty] | Replaced |  |  | YES
5 | 0501-0 |  | 05002A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0501-0 |  | 05003A
5 | 0501-1 |  | 05004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0501-2 |  | 05005A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
5 | 0501-3 |  | 05006A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0502-0 |  | 05007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0502-0 | 12208 | 05008A
5 | 0502-0 |  | 05009A
5 | 0502-1 |  | 05010A |  |  |  | No Cxn |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0502-2 |  | 05011A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
5 | 0502-3 |  | 05012A
5 | 0503-0 | 12243 | 05013A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0503-0 |  | 05014A |  |  |  | No Cxn |  |  |  |  | YES | YES
5 | 0503-0 |  | 05015A
5 | 0503-1 |  | 05016A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0503-2 |  | 05017A | Out | [7 empty] | YES | YES | [5 empty] | 1
5 | 0503-3 |  | 05018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
5 | 0504-0 |  | 05019A
5 | 0504-0 | 12244 | 05020A
5 | 0504-0 |  | 05021A | Loose |  | Loose | [5 empty] | YES | YES | 1
5 | 0504-1 |  | 05022A | [7 empty] | video short
5 | 0504-2 |  | 05023A | [7 empty] | video short
5 | 0504-3 |  | 05024A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0601-0 | 12216 | 06001A
6 | 0601-0 |  | 06002A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
6 | 0601-1 |  | 06003A |  |  |  | No Cxn |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0601-2 |  | 06004A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
6 | 0602-0 |  | 06005A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0602-0 | 12274 | 06006A
6 | 0602-0 |  | 06007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0602-1 |  | 06008A
6 | 0602-2 |  | 06009A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0602-3 |  | 06010A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0603-0 | 12245 | 06011A
6 | 0603-0 |  | 06012A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0603-0 |  | 06013A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0603-1 |  | 06014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0603-2 |  | 06015A
6 | 0603-3 |  | 06016A
6 | 0604-0 | 12225 | 06017A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0604-0 |  | 06018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
6 | 0604-1 |  | 06019A
6 | 0604-2 |  | 06020A |  |  |  | No Cxn |  |  |  |  | YES | YES | [5 empty] | 1
6 | LOUNGE |  | 06021A | [7 empty] | video short
7 | 0701-0 | 12275 | 07001A | [7 empty] | video short
7 | 0701-0 |  | 07002A | Loose | [7 empty] | YES | YES | 1
7 | 0701-0 |  | 07003A
7 | 0701-1 |  | 07004A
7 | 0701-2 |  | 07005A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
7 | 0701-3 |  | 07006A
7 | 0702-0 |  | 07007A
7 | 0702-0 | 12276 | 07008A |  |  |  | In |  |  |  |  | YES | YES |  | 1
7 | 0702-0 |  | 07009A |  |  |  | In |  |  |  | video short | YES | YES | [5 empty] | 1
7 | 0702-1 |  | 07010A |  |  |  | Out |  |  |  |  | YES | YES | [5 empty] | 1
7 | 0702-2 |  | 07011A | Out |  |  | Out |  |  |  |  | YES | YES |  | 1
7 | 0702-3 |  | 07012A
7 | 0703-0 | 12234 | 07013A
7 | 0703-0 |  | 07014A
7 | 0703-0 |  | 07015A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
7 | 0703-1 |  | 07016A
7 | 0703-2 |  | 07017A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
7 | 0703-3 |  | 07018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
7 | 0704-0 |  | 07019A
7 | 0704-0 | 12235 | 07020A | [6 empty] | Replaced |  |  | YES
7 | 0704-0 |  | 07021A
7 | 0704-1 |  | 07022A
7 | 0704-2 |  | 07023A | Out | [7 empty] | YES | YES | [11 empty] | Visit
7 | 0704-3 |  | 07024A
8 | 0801-0 | 12209 | 08001A
8 | 0801-0 |  | 08002A
8 | 0801-1 |  | 08003A
8 | 0801-2 |  | 08004A
8 | 0802-0 |  | 08005A
8 | 0802-0 | 12257 | 08006A |  |  |  | In |  |  |  | 2 red phones | YES | YES | [5 empty] | 1
8 | 0802-0 |  | 08007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
8 | 0802-1 |  | 08008A
8 | 0802-2 |  | 08009A |  |  |  | In |  |  |  |  | YES | YES |  | 1
8 | 0802-3 |  | 08010A | [5 empty] | In |  |  | YES | YES | [5 empty] | 1
8 | 0803-0 | 12236 | 08011A
8 | 0803-0 |  | 08012A
8 | 0803-0 |  | 08013A
8 | 0803-1 |  | 08014A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
8 | 0803-2 |  | 08015A | Loose | [7 empty] | YES | YES | 1
8 | 0803-3 |  | 08016A |  |  |  | Out |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
8 | 0804-0 | 12217 | 08017A | [7 empty] | video short
8 | 0804-0 |  | 08018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
8 | 0804-1 |  | 08019A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
8 | 0804-2 |  | 08020A
8 | LOUNGE |  | 08021A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
9 | 0901-0 | 12258 | 09001A
9 | 0901-0 |  | 09002A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
9 | 0901-0 |  | 09003A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
9 | 0901-1 |  | 09004A |  |  |  | In |  |  |  |  | YES | YES |  | 1
9 | 0901-2 |  | 09005A |  |  |  | Out |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
9 | 0901-3 |  | 09006A
9 | 0902-0 | 12246 | 09007A
9 | 0902-0 |  | 09008A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
9 | 0902-0 |  | 09009A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
9 | 0902-1 |  | 09010A | Loose | [7 empty] | YES | YES
9 | 0902-2 |  | 09011A |  |  |  | In |  |  |  |  | YES | YES
9 | 0902-3 |  | 09012A | [7 empty] | video short
9 | 0903-0 | 12226 | 09013A
9 | 0903-0 |  | 09014A
9 | 0903-0 |  | 09015A
9 | 0903-1 |  | 09016A
9 | 0903-2 |  | 09017A
9 | 0903-3 |  | 09018A
9 | 0904-0 |  | 09019A
9 | 0904-0 | 12218 | 09020A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
9 | 0904-0 |  | 09021A
9 | 0904-1 |  | 09022A
9 | 0904-2 |  | 09023A | Loose | [7 empty] | YES | YES | 1
9 | 0904-3 |  | 09024A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
10 | 1001-0 | 12277 | 10001A
10 | 1001-0 |  | 10002A
10 | 1001-1 |  | 10003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
10 | 1001-2 |  | 10004A
10 | 1002-0 |  | 10005A
10 | 1002-0 | 12247 | 10006A
10 | 1002-0 |  | 10007A
10 | 1002-1 |  | 10008A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
10 | 1002-2 |  | 10009A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
10 | 1002-3 |  | 10010A | Loose | [7 empty] | YES | YES | 1
10 | 1003-0 | 12219 | 10011A
10 | 1003-0 |  | 10012A
10 | 1003-0 |  | 10013A
10 | 1003-1 |  | 10014A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
10 | 1003-2 |  | 10015A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
10 | 1003-3 |  | 10016A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
10 | 1004-0 | 12220 | 10017A |  | Broken | [6 empty] | YES | YES | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
10 | 1004-0 |  | 10018A
10 | 1004-1 |  | 10019A |  |  |  | In |  |  |  |  | YES | YES |  | 1
10 | 1004-2 |  | 10020A | [7 empty] | video short
10 | LOUNGE |  | 10021A |  |  |  |  | In |  |  |  | YES | YES | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
11 | 1101-0 | 12259 | 11001A
11 | 1101-0 |  | 11002A | Loose | [7 empty] | YES | YES | 1
11 | 1101-0 |  | 11003A
11 | 1101-1 |  | 11004A
11 | 1101-2 |  | 11005A | Loose | [7 empty] | YES | YES | [11 empty] | *
11 | 1101-3 |  | 11006A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
11 | 1102-0 |  | 11007A
11 | 1102-0 | 12210 | 11008A |  |  |  | In | No Cxn |  |  |  | YES | YES | [5 empty] | 1 |  |  | 1
11 | 1102-0 |  | 11009A | [7 empty] | short cable jack
11 | 1102-1 |  | 11010A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
11 | 1102-2 |  | 11011A
11 | 1102-3 |  | 11012A
11 | 1103-0 | 12248 | 11013A | Loose | [5 empty] | Replaced | short cable jack and correct extn | YES | YES | 1
11 | 1103-0 |  | 11014A | Loose | [7 empty] | YES | YES | 1
11 | 1103-0 |  | 11015A |  |  |  |  | In | In |  | short cable jack | YES | YES | [5 empty] | 1
11 | 1103-1 |  | 11016A | Loose |  | Loose | [5 empty] | YES | YES | 1 |  |  |  |  | 1
11 | 1103-2 |  | 11017A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
11 | 1103-3 |  | 11018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
11 | 1104-0 |  | 11019A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
11 | 1104-0 | 12266 | 11020A |  |  |  | In |  |  | Replaced | correct extn | YES | YES | [5 empty] | 1
11 | 1104-0 |  | 11021A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
11 | 1104-1 |  | 11022A
11 | 1104-2 |  | 11023A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
11 | 1104-3 |  | 11024A |  |  |  | Stuck |  |  |  |  | YES | YES | [5 empty] | 1
12 | 1201-0 | 12237 | 12001A
12 | 1201-0 |  | 12002A
12 | 1201-1 |  | 12003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
12 | 1201-2 |  | 12004A
12 | 1202-0 |  | 12005A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
12 | 1202-0 | 12238 | 12006A |  |  |  | In |  |  |  |  | YES | YES |  |  |  | 1
12 | 1202-0 |  | 12007A
12 | 1202-1 |  | 12008A
12 | 1202-2 |  | 12009A
12 | 1202-3 |  | 12010A | Loose |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
12 | 1203-0 | 12221 | 12011A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
12 | 1203-0 |  | 12012A | Loose | [7 empty] | YES | YES | 1 |  |  |  |  | 1
12 | 1203-0 |  | 12013A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
12 | 1203-1 |  | 12014A |  |  |  | In |  |  |  |  | YES | YES |  | 1
12 | 1203-2 |  | 12015A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
12 | 1203-3 |  | 12016A
12 | 1204-0 | 12211 | 12017A | [6 empty] | Replaced | correct extn |  | YES
12 | 1204-0 |  | 12018A
12 | 1204-1 |  | 12019A
12 | 1204-2 |  | 12020A
12 | LOUNGE |  | 12021A | Loose | [6 empty] | short cable jack | YES | YES | 1
13 | 1301-0 | 12267 | 13001A | Loose |  |  | In | In |  |  |  | YES | YES | 1
13 | 1301-0 |  | 13002A | [5 empty] | In |  |  | YES | YES | [5 empty] | 1
13 | 1301-0 |  | 13003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
13 | 1301-1 |  | 13004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
13 | 1301-2 |  | 13005A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
13 | 1301-3 |  | 13006A |  |  |  | Out |  |  |  |  | YES | YES |  | 1
13 | 1302-0 |  | 13007A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
13 | 1302-0 | 12268 | 13008A | [6 empty] | Replaced |  |  | YES
13 | 1302-0 |  | 13009A |  |  |  | In |  |  |  |  | YES | YES |  | 1
13 | 1302-1 |  | 13010A
13 | 1302-2 |  | 13011A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
13 | 1302-3 |  | 13012A
13 | 1303-0 | 12249 | 13013A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
13 | 1303-0 |  | 13014A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
13 | 1303-0 |  | 13015A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
13 | 1303-1 |  | 13016A
13 | 1303-2 |  | 13017A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
13 | 1303-3 |  | 13018A | [5 empty] | In |  | short cable jack | YES | YES | [5 empty] | 1
13 | 1304-0 |  | 13019A |  |  |  |  | In |  |  | short cable jack | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
13 | 1304-0 | 12250 | 13020A | [5 empty] | No Cxn |  |  | YES | YES | [8 empty] | 1
13 | 1304-0 |  | 13021A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
13 | 1304-1 |  | 13022A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
13 | 1304-2 |  | 13023A | Loose | [7 empty] | YES | YES | 1
13 | 1304-3 |  | 13024A
14 | 1401-0 | 12239 | 14001A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
14 | 1401-0 |  | 14002A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1401-1 |  | 14003A
14 | 1401-2 |  | 14004A
14 | 1402-0 |  | 14005A |  |  |  |  | In |  |  | short cable jack | YES | YES | [5 empty] | 1
14 | 1402-0 | 12240 | 14006A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1402-0 |  | 14007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1402-1 |  | 14008A
14 | 1402-2 |  | 14009A
14 | 1402-3 |  | 14010A | [7 empty] | short cable jack
14 | 1403-0 | 12292 | 14011A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1403-0 |  | 14012A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1403-0 |  | 14013A | [7 empty] | short cable jack
14 | 1403-1 |  | 14014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1403-2 |  | 14015A | Loose |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1403-3 |  | 14016A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1404-0 | 12286 | 14017A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1404-0 |  | 14018A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
14 | 1404-1 |  | 14019A | [7 empty] | short cable jack
14 | 1404-2 |  | 14020A
14 | LOUNGE |  | 14021A | [5 empty] | In |  | short cable jack | YES | YES | [5 empty] | 1
15 | 1501-0 | 12324 | 15001A | Loose | [7 empty] | YES | YES | 1
15 | 1501-0 |  | 15002A
15 | 1501-0 |  | 15003A | Loose | [7 empty] | YES | YES | 1
15 | 1501-1 |  | 15004A
15 | 1501-2 |  | 15005A |  |  |  | In | In |  |  |  | YES | YES |  | 1
15 | 1501-3 |  | 15006A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
15 | 1502-0 |  | 15007A |  |  |  | No Cxn |  |  |  | short cable jack | YES | YES | [5 empty] | 1
15 | 1502-0 | 12278 | 15008A
15 | 1502-0 |  | 15009A | [5 empty] | In |  |  | YES | YES
15 | 1502-1 |  | 15010A
15 | 1502-2 |  | 15011A
15 | 1502-3 |  | 15012A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
15 | 1503-0 | 12312 | 15013A
15 | 1503-0 |  | 15014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
15 | 1503-0 |  | 15015A | Loose | [7 empty] | YES | YES | 1
15 | 1503-1 |  | 15016A
15 | 1503-2 |  | 15017A |  |  |  | Out |  |  |  |  | YES | YES | [5 empty] | 1
15 | 1503-3 |  | 15018A |  |  |  | In |  |  |  |  | YES | YES |  | 1
15 | 1504-0 |  | 15019A
15 | 1504-0 | 12325 | 15020A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
15 | 1504-0 |  | 15021A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
15 | 1504-1 |  | 15022A
15 | 1504-2 |  | 15023A | Loose |  |  |  | Out |  |  |  | YES | YES | 1 | 1 | 1
15 | 1504-3 |  | 15024A
16 | 1601-0 | 12297 | 16001A
16 | 1601-0 |  | 16002A
16 | 1601-1 |  | 16003A
16 | 1601-2 |  | 16004A
16 | 1602-0 |  | 16005A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1 |  |  | 1
16 | 1602-0 | 12298 | 16006A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
16 | 1602-0 |  | 16007A
16 | 1602-1 |  | 16008A
16 | 1602-2 |  | 16009A | Loose |  |  | No Cxn |  |  |  |  | YES | YES | 1 |  | 1 |  |  | 1
16 | 1602-3 |  | 16010A
16 | 1603-0 | 12287 | 16011A | [7 empty] | short cable jack
16 | 1603-0 |  | 16012A
16 | 1603-0 |  | 16013A
16 | 1603-1 |  | 16014A
16 | 1603-2 |  | 16015A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
16 | 1603-3 |  | 16016A
16 | 1604-0 | 12279 | 16017A
16 | 1604-0 |  | 16018A
16 | 1604-1 |  | 16019A
16 | 1604-2 |  | 16020A
16 | LOUNGE |  | 16021A | Loose | [7 empty] | YES | YES | 1
17 | 1701-0 | 12326 | 17001A
17 | 1701-0 |  | 17002A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1701-0 |  | 17003A
17 | 1701-1 |  | 17004A |  |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
17 | 1701-2 |  | 17005A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1
17 | 1701-3 |  | 17006A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1702-0 |  | 17007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1702-0 | 12327 | 17008A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
17 | 1702-0 |  | 17009A | Loose |  | Loose | [5 empty] | YES | YES | 1
17 | 1702-1 |  | 17010A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
17 | 1702-2 |  | 17011A
17 | 1702-3 |  | 17012A |  |  |  | Out |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
17 | 1703-0 | 12313 | 17013A
17 | 1703-0 |  | 17014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1703-0 |  | 17015A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1703-1 |  | 17016A | [7 empty] | short cable jack
17 | 1703-2 |  | 17017A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1703-3 |  | 17018A | [7 empty] | short cable jack
17 | 1704-0 |  | 17019A
17 | 1704-0 | 12314 | 17020A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1
17 | 1704-0 |  | 17021A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1
17 | 1704-1 |  | 17022A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1704-2 |  | 17023A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
17 | 1704-3 |  | 17024A | Loose | [7 empty] | YES | YES
18 | 1801-0 | 12299 | 18001A
18 | 1801-0 |  | 18002A | [7 empty] | short cable jack
18 | 1801-1 |  | 18003A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
18 | 1801-2 |  | 18004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
18 | 1802-0 |  | 18005A
18 | 1802-0 | 12293 | 18006A
18 | 1802-0 |  | 18007A | [7 empty] | short cable jack
18 | 1802-1 |  | 18008A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
18 | 1802-2 |  | 18009A |  |  |  | In |  |  |  |  | YES | YES |  | 1
18 | 1802-3 |  | 18010A
18 | 1803-0 | 12280 | 18011A
18 | 1803-0 |  | 18012A
18 | 1803-0 |  | 18013A | [7 empty] | short cable jack
18 | 1803-1 |  | 18014A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
18 | 1803-2 |  | 18015A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
18 | 1803-3 |  | 18016A
18 | 1804-0 | 12281 | 18017A
18 | 1804-0 |  | 18018A |  |  |  | In |  |  |  |  | YES | YES |  | 1
18 | 1804-1 |  | 18019A | [7 empty] | short cabel jack
18 | 1804-2 |  | 18020A
18 | LOUNGE |  | 18021A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
19 | 1901-0 | 12315 | 19001A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
19 | 1901-0 |  | 19002A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
19 | 1901-0 |  | 19003A |  |  |  |  | In | In |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  |  | 1
19 | 1901-1 |  | 19004A |  |  |  | In |  |  |  |  | YES | YES |  | 1
19 | 1901-2 |  | 19005A | [7 empty] | short cable jack
19 | 1901-3 |  | 19006A
19 | 1902-0 |  | 19007A
19 | 1902-0 | 12328 | 19008A | [7 empty] | short cable jack
19 | 1902-0 |  | 19009A
19 | 1902-1 |  | 19010A
19 | 1902-2 |  | 19011A
19 | 1902-3 |  | 19012A
19 | 1903-0 | 12306 | 19013A | [7 empty] | short cable jack
19 | 1903-0 |  | 19014A | [7 empty] | short cable jack
19 | 1903-0 |  | 19015A | [7 empty] | short cable jack
19 | 1903-1 |  | 19016A |  |  |  | In |  |  |  |  | YES | YES |  | 1
19 | 1903-2 |  | 19017A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
19 | 1903-3 |  | 19018A
19 | 1904-0 |  | 19019A |  |  |  |  | In |  |  | short cable jack | YES | YES | [6 empty] | 1
19 | 1904-0 | 12316 | 19020A |  |  |  |  | No Cxn |  |  | short cable jack | YES | YES | [8 empty] | 1
19 | 1904-0 |  | 19021A
19 | 1904-1 |  | 19022A |  |  |  | Out |  |  |  |  | YES | YES | [5 empty] | 1
19 | 1904-2 |  | 19023A |  |  |  | In |  |  |  |  | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
19 | 1904-3 |  | 19024A | [7 empty] | short cabel jack
20 | 2001-0 | 12294 | 20001A |  |  |  |  | In |  |  |  | YES | YES | [5 empty] | 1
20 | 2001-0 |  | 20002A
20 | 2001-1 |  | 20003A
20 | 2001-2 |  | 20004A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
20 | 2002-0 |  | 20005A
20 | 2002-0 | 12288 | 20006A
20 | 2002-0 |  | 20007A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
20 | 2002-1 |  | 20008A | Loose | [6 empty] | short cable jack | YES | YES | 1
20 | 2002-2 |  | 20009A | Loose | [7 empty] | YES | YES | 1
20 | 2002-3 |  | 20010A
20 | 2003-0 | 12282 | 20011A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
20 | 2003-0 |  | 20012A | [7 empty] | short cable jack
20 | 2003-0 |  | 20013A | [7 empty] | short cable jack
20 | 2003-1 |  | 20014A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
20 | 2003-2 |  | 20015A |  |  |  | In | In |  |  |  | YES | YES | [5 empty] | 1
20 | 2003-3 |  | 20016A | Loose | [7 empty] | YES | YES | 1
20 | 2004-0 | 12329 | 20017A | [7 empty] | short cable jack
20 | 2004-0 |  | 20018A | Loose | [7 empty] | YES | YES | 1 | 1
20 | 2004-1 |  | 20019A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
20 | 2004-2 |  | 20020A |  |  |  | In |  |  |  |  | YES | YES
20 | LOUNGE |  | 20021A | Loose | [6 empty] | short cable jack | YES | YES |  | 1 | 1 | 1 | 1 |  |  |  | 1
21 | 2101-0 | 12317 | 21001A
21 | 2101-0 |  | 21002A | Loose |  |  | In |  |  |  |  | YES | YES | 1 |  |  |  |  | 1
21 | 2101-0 |  | 21003A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
21 | 2101-1 |  | 21004A
21 | 2101-2 |  | 21005A
21 | 2101-3 |  | 21006A
21 | 2102-0 |  | 21007A
21 | 2102-0 | 12318 | 21008A | Loose | [7 empty] | YES | YES | 1
21 | 2102-0 |  | 21009A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
21 | 2102-1 |  | 21010A | [7 empty] | short cabel jack
21 | 2102-2 |  | 21011A |  |  |  | Out |  |  |  |  | YES | YES | [5 empty] | 1
21 | 2102-3 |  | 21012A
21 | 2103-0 | 12307 | 21013A
21 | 2103-0 |  | 21014A
21 | 2103-0 |  | 21015A |  |  |  | In |  |  |  |  | YES | YES | [5 empty] | 1
21 | 2103-1 |  | 21016A
21 | 2103-2 |  | 21017A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
21 | 2103-3 |  | 21018A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
21 | 2104-0 |  | 21019A
21 | 2104-0 | 12308 | 21020A | Loose |  |  | In |  |  |  |  | YES | YES | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1
21 | 2104-0 |  | 21021A | [7 empty] | short cable jack
21 | 2104-1 |  | 21022A
21 | 2104-2 |  | 21023A
21 | 2104-3 |  | 21026A |  |  |  | In |  |  |  |  | YES | YES |  |  | 1
22 | LOUNGE |  | 22001A
22 | 2212 | 25913 | 22001C | [7 empty] | didn’t check
22 | 2200 |  | 22002A | [7 empty] | didn’t check
22 | PENTHOU | 27521 | 22003A | [7 empty] | didn’t check, locked
464 |  |  |  | 47 | 1 | 3 | 174 | 27 | 9 | 8 |  | 226 | 231 | 39 | 43 | 39 | 25 | 24 | 141 | 2 | 0 | 24 | 2 | 0
|  |  | No Connection |  |  |  | 6 | 2 | 2
|  |  | Stuck |  |  |  | 1 | 0 | 0
|  |  | In | 0 |  |  | 158 | 24 | 7
|  |  | Out | 3 |  |  | 9 | 1 | 0
|  |  | Replaced | [6 empty] | 4
|  |  | Loose | 44 | 0 | 3
|  |  | Missing |  | 0 | 0 |  |  |  | 0
|  |  | Broken |  | 1 |  |  |  |  | 0
RD
1 | 0101-0 | 12212 | 01001A
1 | 0103-0 | 12223 | 01002A
1 | 0103-0 | 25903 | 01002A
Note on Z37: Eric Carpenter July 12 2017 Hoefler report says wall needs to be patched
Note on Z65: Eric Carpenter July 12 2017 Hoefler report says wall needs to be patched
Note on D133: Eric Carpenter July 12 2017 Hoefler says the walls need to be repaired
Note on B145: Eric Carpenter July 12 2017 Hoefler says the walls need to be repaired
Note on Z217: Eric Carpenter: Found a star here on the reports. Not sure what it means.